## ProductBackLog
Project Name: PetPal Group Members: William Ersan ALLAMAND, Damla İNCEBIYIK, Mustafa Eren ŞAHİN, Burcu DUMANLI, Birce ERDOĞAN, Ece KABASAKAL, Kaan DÖNMEZ, Cavit KAYA
# | Product Backlog
1 | Intelligent Feeding Optimization System: the system should automatically adjust feeding portions based on the eating patterns of individual animals. If an animal eats less than usual, the system should alert administrators and suggest portion adjustments.
2 | Environmental Monitoring & Climate Control: The system should include temperature and humidity sensors to monitor the environment of the shelter. If extreme weather conditions are detected, automated ventilation or heating systems should be activated, and administrators should be notified.
3 | Volunteer Scheduling & Management System: The system should allow volunteers to sign up for specific tasks and shifts, ensuring that animal care and feeding are well-coordinated. Automatic reminders should be sent before a shift begins.
4 | AI-Powered Health Prediction: Using historical health data and AI analysis, the system should predict potential health issues in animals before symptoms appear, allowing for early intervention.
5 | Real-Time Animal Tracking: RFID Sensors should update the database with the locations of detected animals every 5 minutes.
6 | Live Map: Users should be able to access a map within the app which displays areas with high animal activity based on the data gathered from the RFID sensors.
7 | Performance and Efficiency Reports: The system must measure the efficiency, response times, processing speeds and identify the areas in need of optimization.
8 | Security: The system must ensure data encryption and security compliance.
9 | Real-Time Notifications and Alerts: The system should notify users when an animal passes an RFID sensor.
10 | User Authentication: The system should support password encryption and multi-factor authentication.
11 | Emergency Veterinary Contact System : The system should automatically alert nearby veterinarians when an animal is reported as sick or injured. Administrators can also manually request emergency assistance through the system.
12 | AI-Based Animal Behavior Analysis : The system should analyze animal movement patterns using AI and alert administrators if unusual behavior is detected, such as reduced movement indicating illness or stress.
13 | Admin Dashboard: Admins should be able to enter the admin dashboard using their account information, see the data they want and change it.
14 | Test Plan: By performing comprehensive error tests in the admin interface, errors and problems are detected and corrected, thus increasing the stability and reliability of the system.
15 | UI/UX Enhancement: The application will be designed to have a simple and understandable user interface that provides easy use of both mobile content (Android/iOS) and the web.
16 | Adoption Requests: Users should be able to submit adoption requests via animal profiles, and administrators should be able to review and resolve these requests.
17 | Database Access: The system should be able to retrieve data from the database and decrypt it accordingly.
18 | Database Backup: The system should perform automatic daily backups for location data and weekly backups for all other data.
19 | Animal Profiles & Health Tracking: Users should be able to access animal profiles by scanning a QR code and report sick or injured animals
20 | Smart Food & Water Bowl Monitoring: The system should track the fill levels of food and water bowls and notify volunteers when levels are low

## Sprint-1
SPRINT-1
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer, Product Owner | Database Planning | In Progress | High | 2025-03-21 | 2025-03-29 | 9 | An efficient and secure database acts as a centralised repository, systematically storing and managing all crucial data.
Developer, Designer | UI / UX Planning & Preparation of UI Templates for Design Purposes | Ready to Start | Medium | 2025-03-27 | 2025-03-29 | 3 | Planning the layout and design of web & mobile apps to ensure a smooth user experience.
Developer | Layout Planning for RFID Sensor Locations | Ready to Start | Low | 2025-03-22 | 2025-03-29 | 8 | Determining the most efficient placement of RFID sensors.
8
BACKLOG
RFID sensors should be placed in bottleneck areas such as staircases, doors, gateways, and paths where animal movement is likely to happen.
STATUS: Ready to Start
As a user, it would be helpful if tutorial videos were made for the mobile app.
STATUS: Ready to Start
QA
User
As a developer, I suggest using caching mechanisms to reduce database load and improve response times.
STATUS: Ready to Start
Dev

## Sprint-2
SPRINT-2
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | Adaptive Feeding System | Not Started | High | 01.04.2025 | 05.04.2025 | 5 | Implement portion adjustment & alerts.
Developer | Environmental Monitoring | Not Started | High | 06.04.2025 | 10.04.2025 | 5 | Integrate sensors, set up climate alerts.
Developer | Volunteer Scheduling System | Not Started | Medium | 11.04.2025 | 14.04.2025 | 4 | Allow volunteers to register & send reminders.
Dev, QA | AI Health Prediction System | Not Started | High | 15.04.2025 | 20.04.2025 | 6 | Train AI model, test accuracy, verify alerts.
20
BACKLOG
As an administrator, I want the system to automatically adjust feeding portions based on individual animals' eating patterns so that their nutritional needs are met.
STATUS: Not Started
As a shelter manager, I want real-time monitoring of temperature and humidity to ensure a safe and comfortable environment for the animals.
STATUS: Not Started
Dev
As a volunteer, I want to sign up for specific tasks and receive reminders so that I can contribute effectively to animal care.
STATUS: Not Started
User
User
As a veterinarian, I want AI-based predictions of potential health issues so that I can intervene early.
STATUS: Not Started
User

## Sprint-3
SPRINT-3
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | Database access | Not Started | High | 2025-04-22 | 2025-04-24 | 3 | Data should be decrypted after retrieving it from the database.
Developer | Animal Location | Not Started | High | 2025-04-22 | 2025-04-26 | 5 | Get locations from RFID and cameras.
Developer | Adoption Requests | Not Started | Medium | 2025-04-26 | 2025-04-28 | 3 | Ask users to fill out a form and send notifications to admins.
Developer | Admin Dashboard | Not Started | Medium | 2025-04-23 | 2025-04-28 | 6 | Admins can see and change the data.
Developer | Database Backup | Not Started | Medium | 2025-04-27 | 2025-04-29 | 3 | Daily backup for locations and weekly backup for everything else.
20
BACKLOG
As a developer, I want to ensure that our application is able to access data from the database, so that it can work properly.
STATUS: Not Started
As a user, I want to submit an adoption request, so that the adoption process becomes more convenient.
STATUS: Not Started
As an admin, I want to know the location of animals, so that procedures like vaccination and adoption can be done easily.
STATUS: Not Started
As an admin, I want to be able to see the data about animals, smart bowls, requests and notifications in one place, so that I can do my job easily.
STATUS: Not Started
As a developer, I want to ensure that database backups are done regularly, so that no data loss occurs in case of a system failure.
STATUS: Not Started
Dev
Dev
Dev
Dev
Dev

## Sprint-4
SPRINT-4
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | İmplement QR Scanning | Ready to Start | High | 2025-05-01 | 2025-05-05 | 5 | Show the animal's health history after scanning the QR .
Developer | Diplace Sensor Data On Admin Panel | In Progress | High | 2025-05-05 | 2025-05-09 | 5 | Display sensor data in hourly graphs.
Developer | Test Plan | Not Started | Medium | 2025-05-07 | 2025-05-10 | 4 | Testing plan and improving reliability.
Dev, Designer | UI & UX Enhancements | Not Started | Medium | 2025-05-10 | 2025-05-14 | 5 | Ensure mobile-friendly, improved UX.
19
BACKLOG
As a user, I want to securely complete my purchase via a trusted payment gateway, so that my transaction is processed safely and I receive immediate confirmation.
STATUS: Not Started
As an admin, I want to access a dashboard that lets me manage books, orders, and users, so that I can efficiently oversee the store’s operations.
STATUS: Not Started
Dev
Dev
As a user, I want the website to be fully responsive and intuitive, so that I enjoy a seamless experience whether I access it via desktop, tablet, or mobile.
STATUS: Not Started
Designer
Dev
As a user, I want to securely complete my purchase via a trusted payment gateway, so that my transaction is processed safely and I receive immediate confirmation.
STATUS: Not Started
As a user, I want to securely complete my purchase via a trusted payment gateway, so that my transaction is processed safely and I receive immediate confirmation.
STATUS: Not Started