## ProductBackLog
Project Name: PetPal Group Members: William Ersan ALLAMAND, Damla İNCEBIYIK, Mustafa Eren ŞAHİN, Burcu DUMANLI, Birce ERDOĞAN, Ece KABASAKAL, Kaan DÖNMEZ, Cavit KAYA
# | Product Backlog
1 | Donation System: Users should be able to make donations via the app by either submitting food at smart feeding stations, or donating money to provide food for animals. In addition, pet food brands should be able to donate food in return for advertisements.
2 | Legal Compliance: The system should comply with any relevant laws.
3 | Volunteer Scheduling & Management System: The system should allow volunteers to sign up for specific tasks and shifts, ensuring that animal care and feeding are well-coordinated. Automatic reminders should be sent before a shift begins.
4 | AI-Powered Health Prediction: Using historical health data and AI analysis of animal behaviour, the system should alert administrators to potential health issues in animals, allowing for early intervention. In addition, users should be able to report animals suspected of having health issues.
5 | Real-Time Animal Tracking: RFID Sensors should update the database with the locations of detected animals every 5 minutes.
6+ | Live Map: Users should be able to access a map within the app which displays areas with high animal activity based on the data gathered from the RFID sensors.
7 | Performance and Efficiency Reports: The system must measure the efficiency, response times, and processing speeds and identify areas in need of optimization.
8 | Security: The system must ensure data encryption and security compliance, along with password encryption and multi-factor authentication.
9 | Real-Time Notifications and Alerts: The system should notify users when nearby feeding stations are low on food and water.
10 | Panic Button: The mobile app UI should include a button big enough to be pressed in a panic. When pressed, the button should list every animal detected by the nearest RFID sensor, allowing the user to select the animal in question, and check vaccination status.
11 | Legacy Support: The mobile app should support older older OS versions as well as new ones.
12 | Offline Functionality: The mobile app should support an offline mode allowing users to access key features such as viewing animal profiles, checking vaccination statuses via QR codes, and submitting adoption requests without a connection, which will be stored locally in the device until they can be sent to the database once a connection has been established.
13 | Admin Dashboard: Admins should be able to enter the admin dashboard using their account information, see relevant information to do with animal profiles, and update or create profiles accordingly.
14 | Testing: By performing comprehensive error tests in the interface and database, errors and problems should be detected and corrected.
15 | UI/UX Usability: The application should be designed to have a simple and understandable user interface that provides easy use for both mobile platforms (Android 14+ / IOS 16+) and the web.
16 | Adoption Requests: Users should be able to submit adoption requests via animal profiles, and administrators should be able to review and resolve these requests.
17 | System Robustness: The system should be able to support enough concurrent users.
18 | Database Backup: The system should perform automatic daily backups for profile related data and weekly backups for all other data. These backups should be performed without service interruption.
19 | Animal Profiles & Health Tracking: Users should be able to access animal profiles by scanning a QR code and report sick or injured animals in addition to checking vaccination status.
20 | Smart Food & Water Bowl Monitoring: The system should track the fill levels of food and water bowls and notify volunteer users when levels are low

## Sprint-1
SPRINT-1
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Dev | Database Planning | In Progress | High | 2025-03-21 | 2025-03-21 | 1 | An efficient and secure database acts as a centralised repository, systematically storing and managing all crucial data.
Dev | UI / UX Planning & Preparation of UI Templates for Design Purposes | Ready to Start | Medium | 2025-03-27 | 2025-03-29 | 3 | Planning the layout and design of web & mobile apps to ensure a smooth user experience.
Dev | Layout Planning for RFID Sensor Locations | Ready to Start | Low | 2025-03-22 | 2025-03-31 | 10 | Determining the most efficient placement of RFID sensors via field research. Also making sure to hide them to prevent theft.
SM, PO | Outlining any laws the system must comply with | Ready to Start | High | 2025-03-20 | 2025-03-20 | 1 | Ensuring this is done early on, and making sure no laws are missed is important, as noticing a law that affects the project at a later stage can be a huge setback.
Dev | Layout Planning for Smart Feeding Stations | Ready to Start | Low | 2025-03-20 | 2025-03-20 | 1 | Feeding stations must be placed away from crowded areas to avoid animal related disturbances.
8
BACKLOG
RFID sensors should be placed in bottleneck areas such as staircases, doors, gateways, and paths where animal movement is likely to happen.
STATUS: Ready to Start
As a user, it would be helpful if tutorial videos were made for the mobile app.
STATUS: Ready to Start
PO
User
As a developer, I suggest using caching mechanisms to reduce database load and improve response times.
STATUS: Ready to Start
Dev

## Sprint-2
SPRINT-2
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Dev | Starting Development of the Mobile App | Not Started | High | 01.04.2025 | 03.04.2025 | 3 | Development of the login screen, and menus for the mobile app.
Dev | Development of Animal Profiles for the Mobile App | Not Started | Low | 03.04.2025 | 03.04.2025 | 1 | Animal profiles should display the name, vaccination status, known health history, age (if known), gender, and any pictures uploaded of the animal.
Dev | Adding Adoption and Report Illness Menus to Animal Profiles | Not Started | Low | 04.04.2025 | 05.04.2025 | 2 | Allow users to send adoption requests or submit a report for injured and sick animals via the app for them to be evaluated by administrators.
Dev | Implementing the Heatmap UI Within the Mobile App | Not Started | Medium | 05.04.2025 | 05.04.2025 | 1 | Ensure that users can identify areas with high animal activity from the map
Dev | Implementing the Panic Button | Not Started | High | 06.04.2025 | 07.04.2025 | 2 | Making sure this can be pressed in a hurry is a must in order to ensure the safety of users.
Dev | Implementing Notifications | Not Started | Low | 07.04.2025 | 07.04.2025 | 1 | Volunteers will be notified when nearby feeding stations are low on food or water.
Dev | Implementing the Offline Mode for the Mobile App | Not Started | Medium | 07.04.2025 | 08.04.2025 | 2 | When offline, data such as adoption requests, illness reports, QR codes and the associated profile data (vaccination status, etc.) for animals, and feeding station locations will be stored locally. When a connection is established, any data stored that needs to be uploaded to the database such as adoption requests and illness reports will be uploaded.
Dev | Legacy Support | Not Started | High | 08.04.2025 | 09.04.2025 | 2 | Ensure that the mobile app works on older versions of Android and IOS.
14
BACKLOG
As a user, I want to be able to enable and disable notifications at will.
STATUS: Not Started
User
As a user, I want to be able to see the live location of an animal I like the profile of, so I can meet the animal in real life before submitting an adoption request.
STATUS: Not Started
User
As a user, I want any UI related to the panic button to be big and bold, to aviod confusion in a tense moment.
STATUS: Not Started
User

## Sprint-3
SPRINT-3
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Dev | Database Integration | Not Started | High | 10.04.2025 | 12.04.2025 | 3 | Implement the database and establish a connection between the application and the database. Data should be decrypted after retrieving it from the database.
Dev | Animal Profile Storage | Not Started | Medium | 12.04.2025 | 12.04.2025 | 1 | Implement functionality to save new animal profiles in the database. Ask users to fill out a form and send notifications to admins accordingly.
Dev | Location Tracking | Not Started | High | 12.04.2025 | 13.04.2025 | 2 | Get location data from RFID sensors and cameras, and store it in the database with 5 minute intervals. Tests will be conducted on a temporary test rig.
Dev | Adoption Requests and Reports | Not Started | Medium | 14.04.2025 | 15.04.2025 | 2 | Make sure the database recieves and stores adoption requests and reports accordingly.
Dev, PO | Admin Dashboard | Not Started | Medium | 16.04.2025 | 16.04.2025 | 1 | Create an admin dashboard for managing animal profiles, adoption requests, and system settings.
Dev | Database Backup | Not Started | Medium | 17.04.2025 | 17.04.2025 | 1 | Daily backup for heatmap data and weekly backup for everything else.
10
BACKLOG
As a developer, I want to ensure that database backups are done regularly, so that no data loss occurs in case of a system failure.
STATUS: Not Started
Dev
Consider user experience when designing the Admin Dashboard, keep the interface simple.
STATUS: Not Started
PO
Run load tests on the database integration to check how it performs under heavy traffic.
STATUS: Not Started
SM
For adoption requests, implement proper validation to avoid spam or duplicate submissions.
STATUS: Not Started
PO

## Sprint-4
SPRINT-4
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Dev | Implement QR Scanning | Not Started | Low | 18.04.2025 | 18.04.2025 | 1 | Show the health history of the animal in question after scanning the QR via the mobile application.
Dev | Smart Feeding Stations Database Integration | Not Started | Medium | 18.04.2025 | 18.04.2025 | 1 | Ensure real-time data transfer between smart feeding stations and the database. The interval should be once per hour. Tests will be conducted on a temporary test rig.
Dev, SM | Testing | Not Started | High | 19.04.2025 | 23.04.2025 | 5 | Testing and improving reliability.
Dev | Security Enhancements | Not Started | High | 19.04.2025 | 21.04.2025 | 3 | Ensure data encryption, password security, and multi-factor authentication.
Dev, PO | Bug Fixes and UI & UX Enhancements | Not Started | High | 22.04.2025 | 23.04.2025 | 2 | Perform debugging and improve the user interface and experience.
Dev | Mounting Feeding Stations and RFID Sensors in Planned Locations | Not Started | High | 24.04.2025 | 30.04.2025 | 7 | Making sure everything is placed properly in the planned locations and connecting each IoT device to the database.
Dev | User Guide Preparation | Not Started | Medium | 01.04.2025 | 01.04.2025 | 1 | Preparing user manuals and tutorial videos to help people understand how to use the mobile application.
Dev, SM, PO | Launching the System | Not Started | High | 02.04.2025 | 02.04.2025 | 1 | Opening the system for public use once we are sure everything works properly.
21
BACKLOG
As an administrator, I would like user guides for the admin panel.
STATUS: Not Started
User